## Overview
Field | Value
Project Name | Data Manager AI
Owner
Start Date | 2025-12-22
Target Completion Date
Reporting Cadence | Weekly
Last Updated | 2025-12-12

## Tasks
Tasks ID | Tasks List | Tasks Category | Task Map | Task Discreption | Assigned To | Start Date | Target Date | Actual End Date | Status | % Complete | Dependencies | Comments
Dashboard | Dashboard | Frontend | Dashboard |  | Arthi/Tejasree | 2026-01-02 | 2026-01-05 | 2026-01-05 | Completed
Study Management | Study Management | Frontend | Study Management |  | Arthi/Tejasree | 2026-01-02 | 2026-01-05 | 2026-01-05 | Completed
Data Integration | Data Integration | Frontend | Data Integration |  | Arthi/Tejasree | 2026-01-05 | 2026-01-07 |  | In Progress
Trail Data Management | Trail Data Management | Frontend | Trail Data Management |  | Arthi/Tejasree | 2026-01-05 | 2026-01-08 |  | In Progress
Data Manager.AI | Data Manager.AI | Frontend | Data Manager.AI |  | Arthi/Tejasree | 2026-01-05 | 2026-01-08 |  | In Progress
DB Schema - Dashboard | DB Schema - Dashboard | Database | Dashboard |  | Ritesh | 2026-01-02 | 2025-01-06 | 2025-01-06 | Completed
DB Schema - Study Management | DB Schema - Study Management | Database | Study Management |  | Ritesh | 2026-01-06 | 2026-01-07 |  | In Progress
DB Schema - Data Integration | DB Schema - Data Integration | Database | Data Integration |  | Deepta | 2026-01-05 | 2026-01-06 | 2026-01-06 | Completed
DB Schema - Trail Data Management | DB Schema - Trail Data Management | Database | Trail Data Management |  | Ritesh | 2026-01-06 | 2026-01-07 |  | In Progress
DB Schema - DataManager.AI | DB Schema - DataManager.AI | Database | Data Manager.AI |  | Hanif | 2026-01-06 | 2026-01-07 |  | In Progress
Populate Trail Data into PostgreSQL | Populate Trail Data into PostgreSQL | Database | Trail Data Management | Populate EDC Data(DM,SV,DS,AE...) into PostgreSQL | Ruthra | 2026-01-08 | 2026-01-09 |  | In Progress
Study Management - CRUD - DB | Study Management - CRUD - DB | Backend | Study Management | User should be able to create new studies, sites,studycontacts, vendors, documents. | Priyeshwer |  |  |  | In Progress
Creating and Integrate PostgreSQL DBs | Creating and Integrate PostgreSQL DBs | Backend | Data Integration |  | Priyeshwer |  |  |  | Completed
Make Refresh, Pause, Actions - Dynamic | Make Refresh, Pause, Actions - Dynamic | Backend | Data Integration |  | Priyeshwer |  |  |  | Completed
Scheduler | Scheduler | Backend | Data Integration |  | Deepta |  |  |  | Completed
Integrate Integration Logs | Integrate Integration Logs | Backend | Data Integration |  | Priyeshwer |  |  |  | Not Started
Build Data Quality Checks Agent | Build Data Quality Checks Agent | Backend | Data Manager.AI |  | Ruthra/Hanif |  |  |  | Not Started
Build Reconcilation Agent | Build Reconcilation Agent | Backend | Data Manager.AI |  | Ruthra/Hanif |  |  |  | Not Started
Data Fetch Agent | Data Fetch Agent | Backend | Data Manager.AI |  | Ruthra/Hanif |  |  |  | Not Started
DQ Processing Agent | DQ Processing Agent | Backend | Data Manager.AI |  | Ruthra/Hanif |  |  |  | Not Started
Protocol Check Agent | Protocol Check Agent | Backend | Data Manager.AI |  | Ruthra/Hanif |  |  |  | Not Started
Task Manager Agent | Task Manager Agent | Backend | Data Manager.AI |  | Ruthra/Hanif |  |  |  | Not Started
Test Study Management | Test Study Management | Backend | Study Management |  | Ritesh |  |  |  | Not Started
Test Data Integration | Test Data Integration | Backend | Data Integration |  | Ritesh |  |  |  | Not Started
Test Trail Data Management | Test Trail Data Management | Backend | Trail Data Management |  | Ritesh |  |  |  | Not Started
Test Data Manager.AI | Test Data Manager.AI | Backend | Data Manager.AI |  | Ritesh |  |  |  | Not Started
Maintain Complete Workflow | Maintain Complete Workflow | Backend | Data Manager.AI |  | Ritesh |  |  |  | Not Started
Real-Time Monitoring | Real-Time Monitoring | Backend | Data Integration |  | Aarthi |  |  |  | Not Started
Monitor.ai/Notifications | Monitor.ai/Notifications | Backend | Data Integration |  | Deepta/Tejashree |  |  |  | Not Started

## Milestones
Milestone | Owner | Target Date | Actual Date | Status | Comments
Front End
Back End
Front End
Database
API Integration
Cloud Migration
Agent Orchestration | Mitul
Business Rules | Prabhakar |  |  | Not Started | discuss for better Rules engine
Cloud CI-CD Set-up
Creating separeate Azure cluster | Mitul
Send Team email ID | Eswar | done
Access to Azure Portal | STG Team
Subscriton ID | Mitul
Connect with STG team with SubscriotionID | Eswar & Mitul | not done
Contributor Access to Eswar and Prabhakar | Mitul | not done
Contributor access role Training to ESWAr and Prabhakar | Mitul
Azure Pipeline creation | Mitul
Git Repo switch to Azure Repo | Mitul
.ENV files to Mitul | Eswar | not done
Meet with Venkata and Team
Rule Engine

## Risks_Issues
ID | Risk / Issue | Type (Risk/Issue) | Impact | Likelihood | Severity (=Impact x Likelihood) | Mitigation / Action | Owner | Target Date | Status
Azure license
Resource Group needs to be created
Postgress
Python fast API
Gemini 2.5 Flash /dummy data
Azure Data Foundry - Production/POC
Multi-LLMS/Multi-Agents ?
Notes
Azure Access
| Azure PostgreSQL DB | Risk
| Azure Blob Storage | Risk
| Azure Key Vault | Risk
| Azure App Services | Risk
| Azure Monitor | Risk
| Azure Logic Apps | Risk
Application Insights
Open -AI and Orchestration | Azure Foundry
RAG | Azure-AI Search
RADIS Cache
User Management | Entra ID / Hexaware SSO/Client SSO
API Subnet
Agent Orchestration | Symeantic Kernel
Azure documents
Front END | React
AI | FAST API
Database | Postgress

## Metrics
Metric | Value
Total Tasks | 30
Completed Tasks
In Progress Tasks | 8
Not Started Tasks
On Hold Tasks
Overdue Tasks
% Completion (Weighted by % Complete) | 0

## Team Work Challenges
Date | Task | Task Details | Who | Resolved (Yes/No) | Resolved By?

## Sheet1
Date | Task | status
2026-01-05 | Update Target dates
start business rules
Update Task Map- Datamanager,Central Monitor
Effort Tracker
Daily Task Tracker-
Update Task Start date

## Sheet3
Count of Status | Status
Tasks Category | Completed | In Progress | Not Started | (blank) | Grand Total
Backend |  | 1 | 17 |  | 18
Database | 2 | 4 |  |  | 6
Frontend | 2 | 3 |  |  | 5
(blank)
Grand Total | 4 | 8 | 17 |  | 29

## Sheet7
Tasks Category | Completed | In Progress | Not Started
Backend |  | 1 | 17
Database | 2 | 4
Frontend | 2 | 3

## Sheet4
Assigned To | Count of Assigned To
Ritesh | 8
Ruthra/Hanif | 6
Arthi/Tejasree | 5
Priyeshwer | 4
Deepta | 2
Ruthra | 1
Aarthi | 1
Deepta/Tejashree | 1
Hanif | 1
Grand Total | 29

## Sheet5
Count of Assigned To | Status
Assigned To | Not Started | In Progress | Completed | Grand Total
Ritesh | 5 | 2 | 1 | 8
Ruthra/Hanif | 6 |  |  | 6
Arthi/Tejasree |  | 3 | 2 | 5
Priyeshwer | 3 | 1 |  | 4
Deepta | 1 |  | 1 | 2
Ruthra |  | 1 |  | 1
Aarthi | 1 |  |  | 1
Deepta/Tejashree | 1 |  |  | 1
Hanif |  | 1 |  | 1
Grand Total | 17 | 8 | 4 | 29

## Sheet6
Count of Tasks Category |  | Status
Tasks Category | Assigned To | Not Started | In Progress | Completed | Grand Total
Backend | Ruthra/Hanif | 6 |  |  | 6
| Ritesh | 5 |  |  | 5
| Priyeshwer | 3 | 1 |  | 4
| Deepta | 1 |  |  | 1
| Aarthi | 1 |  |  | 1
| Deepta/Tejashree | 1 |  |  | 1
Backend Total |  | 17 | 1 |  | 18
Database | Ritesh |  | 2 | 1 | 3
| Ruthra |  | 1 |  | 1
| Deepta |  |  | 1 | 1
| Hanif |  | 1 |  | 1
Database Total |  |  | 4 | 2 | 6
Frontend | Arthi/Tejasree |  | 3 | 2 | 5
Frontend Total |  |  | 3 | 2 | 5
Grand Total |  | 17 | 8 | 4 | 29