## Overview
Field | Value
Project Name | Data Manager AI
Owner
Start Date | 2025-12-22
Target Completion Date
Reporting Cadence | Weekly
Last Updated | 2025-12-12

## Tasks
Tasks List | Tasks Category | Task Description | Assigned To | Start Date | Target Date | Actual End Date | Status | % Complete | Dependencies | Comments | Days
Dashboard | Frontend (f-01) |  | Aarthi, Tejashree |  |  |  | Completed
Study Management | Frontend (f-02) |  | Aarthi, Tejashree |  |  |  | Completed
Data Integration | Frontend (f-03) |  | Aarthi, Tejashree |  |  |  | In Progress
Trial Data Management | Frontend (f-04) |  | Aarthi, Tejashree |  |  |  | In Progress
Data Manager.AI | Frontend (f-05) |  | Aarthi, Tejashree |  |  |  | In Progress
Central Monitor.AI | Frontend (f-06) |  | Aarthi, Tejashree |  |  |  | Not Started
Signal Detection | Frontend (f-07) |  | Aarthi, Tejashree |  |  |  | Not Started
Task Management | Frontend (f-08) |  | Aarthi, Tejashree |  |  |  | Not Started
Profile Management | Frontend (f-09) |  | Aarthi, Tejashree |  |  |  | Not Started
Reporting and Analytics | Frontend (f-10) |  | Aarthi, Tejashree |  |  |  | Not Started
Notifications | Frontend (f-11) |  | Aarthi, Tejashree |  |  |  | Not Started
Admin | Frontend (f-12) |  | Aarthi, Tejashree |  |  |  | Not Started
Postgres DB to Store Study Data | Database L1 (DB-L-01) |  | Ruthra, Priyeshwar |  |  |  | Completed
Run Reconcilation | Backend [Agent 3] |  | Hanif
Local Folder to Store EDC Data [excel] | Database L1 (DB-L-02) |  | Ruthra, Priyeshwar
Integrate a Local Folder to Ingest EDC Data[excel] - Through UI by Providing Local folder Path | Backend (b-01) |  | Ruthra, Priyeshwar
Understand and Classify the Data - Based on Data Source ID | Backend [Agent 1] |  | Ruthra, Priyeshwar
Store the Agent Classified Data in Local | Database L1 (DB-L-03)
Run DQ Checks | Backend [Agent 2] |  | Hanif
Integrate the Data endpoints to UI - Trail Data Management | Backend (b-02) |  | Ritesh
Task Assignment Agent | Backend [Agent 4]
Technical doubts
Ticket raised
Frontend
Cloud DataBase
Backend

## Milestones
Milestone | Owner | Target Date | Actual Date | Status | Comments
Front End
Back End
Front End |  |  |  | In Progress
Database
API Integration
Cloud Migration
Agent Orchestration
Business Rules

## Risks_Issues
ID | Risk / Issue | Type (Risk/Issue) | Impact | Likelihood | Severity (=Impact x Likelihood) | Mitigation / Action | Owner | Target Date | Status
Azure license
Resource Group needs to be created
Postgress
Python fast API
Gemini 2.5 Flash /dummy data
Azure Data Foundry - Production/POC
Multi-LLMS/Multi-Agents ?
Azure Access
| Azure PostgreSQL DB | Risk
| Azure Blob Storage | Risk
| Azure Key Vault | Risk
| Azure App Services | Risk
| Azure ML | Risk
| Azure Logic Apps | Risk

## Metrics
Metric | Value
Total Tasks | 24
Completed Tasks | 3
In Progress Tasks | 3
Not Started Tasks | 7
On Hold Tasks | 0
Overdue Tasks | 0%
% Completion (Weighted by % Complete) | 0

## Team Work Challenges
Date | Task | Task Details | Who | Resolved (Yes/No) | Resolved By?