## Overview
Field | Value
Project Name | Data Manager AI
Prepared By | Eswara Venkata Sai Raja
Start Date | 2026-02-10
Target Completion Date | 2026-05-20
Reporting Cadence | Weekly
Last Updated | 2026-06-05

## Tasks
Tasks ID | Tasks Lis (Discription) | Task Units | Tasks Category | Task Map/Milestone | Assigned To | Start Date | Target Date | Actual End Date | Status | % Complete | Dependencies | Comments
UserStory (US-1) / TestCases (TC-1) | Create User Stories / Test Cases for Dashboard |  | UserStories | Management | Sai Riteshwar | 2026-01-16 | 2026-01-16 | 2026-01-16 | Completed | 100
UserStory (US-2) / TestCases (TC-2) | Create User Stories / Test Cases for Study Management |  | UserStories | Management | Deepta C S, Aarthi | 2026-01-16 | 2026-01-16 | 2026-01-16 | Completed | 100
UserStory (US-3) / TestCases (TC-3) | Create User Stories / Test Cases for Data Integration |  | UserStories | Management | Priyeshwar | 2026-01-16 | 2026-01-16 | 2026-01-16 | Completed | 100
UserStory (US-4) / TestCases (TC-4) | Create User Stories / Test Cases for Trail Data Management |  | UserStories | Management | Ruthra | 2026-01-16 | 2026-01-16 | 2026-01-16 | Completed | 100
UserStory (US-5) / TestCases (TC-5) | Create User Stories / Test Cases for DataManager |  | UserStories | Management | Hanif, Ruthra | 2026-01-16 | 2026-01-16 | 2026-01-16 | Completed | 100
React Learnings | Refresh All The React Topics In Depth |  | Learnings | Learnings | Aarthi, Deepta,Ruthra | 2026-01-16 | 2026-01-20 | 2026-01-20 | Completed | 100
Node Learnings | Refresh All The Node Topics In Depth |  | Learnings | Learnings | Sai Riteshwar, Tejashree, Priyeshwar, Hanif | 2026-01-16 | 2026-01-20 | 2026-01-20 | Completed | 100
Python Learnings | Refresh All The Python and Agentic Topics In Depth |  | Learnings | Learnings | Aarthi, Deepta,Ruthra, Sai Riteshwar, Tejashree, Priyeshwar, Hanif | 2026-01-20 | 2026-01-23 | 2026-01-23 | Completed | 100
Azure Learnings | Refered Azure Devops Concepts and Azure Services |  | Learnings | Learnings | Aarthi, Deepta,Ruthra, Sai Riteshwar, Tejashree, Priyeshwar, Hanif | 2026-01-20 | 2026-01-23 | 2026-01-23 | Completed | 100
Industrial Standerds Document - Good Practices | Refering Docs |  | Documentation | Documentation | Aarthi, Deepta,Ruthra, Sai Riteshwar, Tejashree, Priyeshwar, Hanif | 2026-02-05 | 2026-02-06 | 2026-02-06 | Completed | 100
Technical Document | Refering Docs |  | Documentation | Documentation | Aarthi, Deepta,Ruthra, Sai Riteshwar, Tejashree, Priyeshwar, Hanif | 2026-02-06 | 2026-02-07 | 2026-02-07 | Completed | 100
Study Management | Make Study Management Functional |  | Frontend | Study Management | Aarthi, Deepta,Ruthra, Sai Riteshwar, Tejashree, Priyeshwar, Hanif | 2026-02-03 | 2026-02-06 | 2026-02-06 | Completed | 100
Integrating PostgreSQL System | Integrating PostgreSQL System |  | DataBase | Data Integration | Hanif, Ritesh | 2026-01-26 | 2026-01-29 | 2026-01-29 | Completed | 100
Storing Clinical Data In Azure PostgreSQL | Store Oncology Data into Azure PostgreSQL |  | Backend | Data Integration | Hanif, Ritesh | 2026-02-06 | 2026-02-09 | 2026-02-09 | Completed | 100
Showcasing Clinical Data in Trial Data Management | Showcasing Clinical Data in Trial Data Management |  | Trial Data Management | Trial Data Management | Hanif, Ritesh | 2026-01-29 | 2026-02-03 | 2026-02-03 | Completed | 100
Dashbard UI Refactoring | Reorganized the dashboard into a task-centric "Workbench" to consolidate tasks, queries, and issues. |  | Frontend | Dashboard | Ruthra | 2026-01-30 | 2026-02-02 | 2026-01-30 | Completed | 100
Integrating Clinical Data to Data Fetch Agent | Ingesting Data from DB to Data Fetch Agent |  | Backend | Data Manager | Tejashree | 2026-02-02 | 2026-02-03 | 2026-02-03 | Completed | 100
Implementing Data Fetch Agent to Flag DQs | Implementing Data Fetch Agent locally using Gemini API Key |  | Backend | Data Manager | Aarthi, Deepta,Tejashree | 2026-02-05 | 2026-02-10 | 2026-02-09 | Completed | 100
Code Conversion | Convert the Fast API Code to NodeJS |  | Frontend/Backend | PIT | Ruthra | 2026-01-26 | 2026-01-27 | 2026-01-26 | Completed | 100
Integrate PI to DM | Integrate Protocol Interpritation tool to Data Manager |  | Frontend/Backend | PIT | Priyeshwar | 2026-02-09 | 2026-02-11 | 2026-02-10 | Completed | 100
Protocol Table Extraction Migration | Migrated manual extraction logic to Azure AI Document Intelligence for high-fidelity clinical table parsing. |  | AI Intelligence | PIT | Ruthra |  |  |  | Completed | 100
DataManger/PIT Code Push | Push The Updated DataManger code to Azure Repo |  | Cloud | Data Manager | Priyeshwar | 2026-02-11 | 2026-02-12 | 2026-02-12 | Completed | 100
Current Code Update | Updating current to multiple protocol |  | Backend | Data Manager | Ruthra | 2026-02-11 |  |  | Completed | 100
Create Test Data | Create Test Data for Oncology with same Subject ID, Vist ID, Site ID and Manipulate few Data Values for testing and also Increase the number of subjects. |  | DataBase | Data Manager | Aarthi, Tejashree | 2026-02-12 | 2026-02-13 |  | Completed | 100
Create Protocol Document | Create Protocol Document which is related to the Original Oncology Dataset. |  | DataBase | Data Manager | Deepta C S | 2026-02-12 | 2026-02-13 |  | Completed | 100
Test Azure AI Foundry Service | Create a Sample Test Agent in Local Integrate it with the Gpt4o model which was created in Azure AI Foundry |  | Cloud | Data Manager | Hanif | 2026-02-12 | 2026-02-13 |  | Completed | 100
Push the Working DataManager code to Repo |  |  | Cloud | Data Manager | Hanif | 2026-02-12 | 2026-02-12 | 2026-02-13 | Completed | 100
Integrate PIT to DataManager |  |  | Frontend/Backend | Data Manager | Priyeshwar | 2026-02-12 | 2026-02-15 | 2026-02-14 | Completed | 100
Serverless DB for API Data Integration / Ingest the Clinical Trail Data and Test Data | Look Into Various Serverless DB Platforms [Turso] - Test the Integration Code Dynamic. |  | DataBase | Data Manager | Sai Riteshwar | 2026-02-12 | 2026-02-15 | 2026-02-13 | Completed | 100
UserStory3: [FE: Study List & Create Study UI] - Study Management UI | Review Study Management Code End to End and Update if any Modifications, Studies Data Should be stored in Azure PostgreSQL |  | Frontend | Study Management | Ruthra, Priyeshwar | 2026-02-13 | 2026-02-16 | 2026-02-16 | Completed | 100
UserStory4: [FE: Study Details Page (Protocol Status + Requirements Status)] | Wipe out the unwanted codeds in Study Management Backed |  | Backend | Study Management | Hanif, Ritesh | 2026-02-13 | 2026-02-16 |  | Completed | 100
Look into DataManager.AI Feature Code | Look into DataManager.AI Feature Code and make a note of all the endpoints and the functions names. |  | Backend | DataManger | Tejashree,Aarthi | 2026-02-16 | 2026-02-16 | 2026-02-16 | Completed | 100
Data Population | Populated the oncology data into the PostgreSQL database to enable discrepancy flaggingin the Data Manager |  | Database | Data Manager | Tejashree,Aarthi,Deepta | 2026-02-17 | 2026-02-20 | 2026-02-19 | Completed | 100
Data Fetch Agent | Testing the data in Data Fetch Agent |  | Database | Data Manager | Tejashree,Aarthi,Deepta | 2026-02-23 | 2026-02-25 |  | Completed | 100
Running web and backend pipeline |  |  | Cloud | Data Manager | Priyeshwar,Ruthra,Hanif,Ritesh | 2026-02-16 | 2026-02-23 | 2026-02-22 | Completed | 100
Running agent pipeline |  |  | Cloud | Data Manager | Priyeshwar,Ruthra,Hanif,Ritesh | 2026-02-16 | 2026-02-23 | 2026-02-23 | Completed | 100
Creating Test Data Based on Protocol Document | Take the referance of Protocol sample Document and Dataset |  |  |  | Aarthi,Tejashree | 2026-02-27 | 2026-03-02 | 2026-03-03 | Completed
Plan for building Task Manager Agent | Review and note down what all the features are dependent on taks manager agent |  |  | Data Manager | Deepta C S | 2026-02-27 | 2026-03-02 |  | Completed
Test Run DQ Agent | Note Down whether we are able to flag and give the outputs as expected or not |  |  |  | Tejashree,Aarthi | 2026-03-27 | 2026-03-27 | 2026-03-27 | Completed | 100
Data fetch Agent / Integration logs |  |  | Frontend/Backend | Data Manager | Priyeshwar | 2026-02-27 | 2026-03-03 | 2026-03-02 | Completed | 100
Task Manager and Task Management Feature | Review and note down what all the features are dependent on taks manager agent |  |  |  | Ruthra | 2026-03-09 |  | 2026-03-11 | Completed | 40
Study Management Protocol Upload | Connecting Azure blob to the study management and uploading protocol to each studies |  | Frontend/Cloud | Study Management | Hanif | 2026-02-26 | 2026-03-03 | 2026-03-03 | Completed | 100
Trail Data Management Issues and Scheduler |  |  | Frontend/Backend |  | Ritesh | 2026-02-27 | 2026-03-03 |  | Completed | 100
Creating Documentation for Test Dataset | Documented the Oncology Test Dataset in accordance with the protocol sample and the rule engine |  | Documentation | Data Manager | Aarthi,Tejashree | 2026-03-04 | 2026-03-05 | 2026-03-05 | Completed | 100
Identify and Flag Missing Data Based on Configuration Settings | Detect and flag missing or incomplete data entries based on predefined configuration rules |  | Frontend/Backend | Data Manager | Tejashree | 2026-03-04 | 2026-03-06 | 2026-03-06 | Completed | 100
Update Dashboard UI to Display Total Data Quality Issues | Update the UI dashboard to reflect the total number of issues found during data quality agent execution. |  | Frontend/Backend | Data Manager | Tejashree, Deepta | 2026-03-09 | 2026-03-10 |  | Completed
Database Schema Alignment | Synchronized local and cloud database schemas to resolve missing table errors (e.g., 'resources' table). |  | Backend/Database |  | Ruthra | 2026-03-11 | 2026-03-13 | 2026-03-13 | Completed | 100
Identify and Flag out of range values based on Configuration settings |  |  | Frontend/Backend | Data Manager | Tejashree | 2026-03-09 | 2026-03-11 | 2026-03-10 | Completed | 100
Identify and Flag Data inconsistency based on Configuration settings |  |  | Frontend/Backend | Data Manager | Aarthi | 2026-03-09 | 2026-03-11 | 2026-03-10 | Completed | 100
Identify and Flag Invalid Format Detection based on Configuration settings |  |  | Frontend/Backend | Data Manager | Aarthi | 2026-03-09 | 2026-03-11 | 2026-03-12 | Completed | 100
Database Schema Updates for DQ Rules | Modify PostgreSQL schema to store trial-specific Data Quality (DQ) rule configurations. |  | Database | Data Manager | Ruthra | 2026-03-09 |  | 2026-03-10 | Completed | 100
Settings Configuration APIs | Develop backend REST APIs to save and retrieve user settings for DQ rules. |  | Backend | Study Management | Ruthra | 2026-03-09 |  | 2026-03-10 | Completed | 100
Settings UI Enhancements | Integrate dynamic severity dropdowns into the DataMonitor AI Settings UI. |  | Frontend | Data Manager | Ruthra | 2026-03-09 |  | 2026-03-11 | Completed | 100
Dynamic Severity Validation Engine | Update the backend validation engine to map user-configured severities to generated discrepancies. |  | Backend | Data Manager | Ruthra | 2026-03-09 |  | 2026-03-11 | Completed | 100
Dynamic Dashboard Data Integration | Refactor the DataMonitor dashboard to pull live discrepancy data from the API instead of mock data. |  | Full Stack | Dashboard | Ruthra | 2026-03-06 |  | 2026-03-09 | Completed | 100
Nomenclature Refactoring (Trials to Studies): | Perform system-wide refactoring to migrate the application nomenclature from 'Trials' to 'Studies'. |  | Code Refactoring | Study Management | Ruthra | 2026-02-25 |  | 2026-02-28 | Completed | 100
Removing CRI, Central Monitor.AI tab in UI |  |  | Frontend | Data Manager | Priyeshwar | 2026-03-02 | 2026-03-06 | 2026-03-04 | Completed | 100
Role Definition for Task Manager | Defining roles with description for TaskManager, transforming the finalized role definitions into JSON |  | Backend | Task Management | C.S.Deepta | 2026-03-09 | 2026-03-11 | 2026-03-10 | Completed | 100
Creating new users login credentials for the Admin console | System Admin can create multiple new users for login credentials |  | Backend | Admin | Hanif | 2026-03-06 | 2026-03-10 |  | Completed
Mapping new users with their Roles, Studies and Access management | Assigning roles to users and allowing access to specific studies |  | Backend | Admin | Hanif | 2026-03-06 | 2026-03-10 |  | Completed
User management controls for System Admin | Providing functios such as Edit user, Activate/Deactivate user, Reset password and Delete user |  | Backend | Admin | Hanif | 2026-03-06 | 2026-03-10 |  | Completed
Fetching rules for Protocol Check |  |  | Backend | Protocol Checks Agent | Ritesh, Priyeshwar | 2026-03-10 | 2026-03-20 | 2026-03-19 | Completed | 100
Validating data with the rules for Protocol Check |  |  | Backend | Protocol Checks Agent | Ritesh, Priyeshwar | 2026-03-10 | 2026-03-20 | 2026-03-19 | Completed | 100
Making Protocol Check UI Funtional |  |  | Frontend | Protocol Checks Agent | Priyeshwar | 2026-03-10 | 2026-03-20 | 2026-03-19 | Completed | 100
Design Issue-to-Role Mapping Logic | Implemented logic to map DQ and Reconciliation issues to specific roles using the roles.json configuration file. |  | Backend | User Management | C.S.Deepta | 2026-03-12 | 2026-03-18 | 2026-03-16 | Completed
Implement Data Quality Issue Generation | Developed functionality to generate DQ issues dynamically when validation checks are executed. |  | Backend | Data Quality (DQ)- rules,Orchastrate | C.S.Deepta | 2026-03-09 | 2026-03-14 | 2026-03-11 | Completed
Automate Task Creation from Issues | Implemented automatic task generation for every DQ or reconciliation issue detected |  | Backend | Task Manager Agent (phase 1 & Phase 2) | C.S.Deepta | 2026-03-16 | 2026-03-20 | 2026-03-18 | Completed
Configure Task Assignment Based on Roles | Enabled role-based task assignment using mappings defined in the role configuration file. |  | Backend | Task Manager Agent (phase 1 & Phase 2) | C.S.Deepta | 2026-03-16 | 2026-03-20 | 2026-03-20 | In Progress
Develop Dynamic Task Manager Integration | Integrated generated tasks with the Task Management module so they appear in the “All Queries and Tasks” table dynamically. |  | Backend | Task Manager Agent (phase 1 & Phase 2) | C.S.Deepta | 2026-03-18 | 2026-03-25 | 2026-03-23 | Completed
Implement Severity-Based Priority System | Configured task priority based on validation severity levels defined in system settings. |  | Backend | DataManager.AI | C.S.Deepta | 2026-03-19 | 2026-03-25 | 2026-03-24 | Completed
Implement Automatic Due Date Logic | Developed functionality to automatically set task due days based on priority |  | Backend | DataManager.AI | C.S.Deepta | 2026-03-17 | 2026-03-25 | 2026-03-20 | Completed
Develop Dynamic "Due In" Calculation | Implemented dynamic calculation of remaining days for each task, updating daily. |  | Backend | DataManager.AI | C.S.Deepta | 2026-03-17 | 2026-03-25 | 2026-03-20 | Completed
Database update in tables for task allocation and storage | Created new database tables to store the respective fetched and allocated values |  | DataBase | Task Manager Agent (phase 1 & Phase 2) | C.S.Deepta | 2026-03-20 | 2026-03-27 | 2026-03-24 | Completed
Enable Dynamic Functionality | Implemented a dynamic view to display all tasks with complete details including study, domain, record ID and source. |  | Backend | Task Manager Agent (phase 1 & Phase 2) | C.S.Deepta | 2026-03-19 | 2026-03-25 | 2026-03-25 | Completed
Prepare Database for Dynamic Task flow | Making the entire Task Management process allign and work respectively with the new dynamic workflow |  | Backend | Task Manager Agent (phase 1 & Phase 2) | C.S.Deepta | 2026-03-18 | 2026-03-25 | 2026-03-25 | Completed
Create Schema and Table for Issue Table | Created a table called issues to store the DQ and reconcilation flagged data |  | Database | Data Manager | Tejashree | 2026-03-10 | 2026-03-12 | 2026-03-12 | Completed | 100
Push the DQ flagged data in the Issue Table |  |  | Backend |  | Tejashree | 2026-03-13 | 2026-03-16 | 2026-03-13 | Completed | 100
Display the total number of Data‑quality issues in the dashboard | Enhanced the dashboard by implementing functionality to display the total number of data‑quality issues |  | Frontend/Backend |  | Aarthi | 2026-03-11 | 2026-03-12 | 2026-03-12 | Completed | 100
Display the study‑based filtering for Data-quality Issues in the dashboard | Implemented study‑based filtering for Data-quality Issues in the dashboard using data retrieved from Study Management dynamically |  | Frontend/Backend |  | Aarthi | 2026-03-12 | 2026-03-13 | 2026-03-13 | Completed | 100
Integrate DQ agent's code from Teja and Aarthi's branch | Merge the DQ agent code from Teja’s branch into Aarthi’s branch, resolve all merge conflicts, and then push the updated branch to Azure. |  | Backend |  | Tejashree,Aarthi | 2026-03-16 | 2026-03-18 | 2026-03-17 | Completed | 100
Integrate Data Manager UI from Ruthra’s Branch with Updated DQ Agent Code |  |  | Backend |  | Tejashree,Aarthi | 2026-03-17 | 2026-03-18 | 2026-03-18 | Completed | 100
Audit Logs in Admin console | Audit log to track every activity of every user inside the data manager application |  | Backend |  | Hanif | 2026-03-11 | 2026-03-13 | 2026-03-13 | Completed | 100
Filtering logs based on multiple parameters | Filtering audit logs based on time, user, event type and severity |  | Backend |  | Hanif | 2026-03-11 | 2026-03-13 | 2026-03-13 | Completed | 100
Actions tab menu and export logs | Actions tab menu to get detailed view on the logs and to export the logs to local |  | Backend |  | Hanif | 2026-03-11 | 2026-03-13 | 2026-03-13 | Completed | 100
Creating multiple roles through admin | System admin can create new role and and this role can be assigned to the users |  | Backend |  | Hanif | 2026-03-16 | 2026-03-17 | 2026-03-17 | Completed | 100
Modifying and deleting role through admin | Newly created role can be modified and can be deleted |  | Backend |  | Hanif | 2026-03-16 | 2026-03-17 | 2026-03-17 | Completed | 100
ER -1 | Created ER diagram for the entire database and created required support files for development usage |  | Documentation |  | Ruthra | 2026-03-09 |  | 2026-03-11 | Completed
Implement the Add Config functionality in the DataManager.ai user interface | Implemented the Add Config functionality in the DataManager.ai ui, allowing users to add the title and description for data quality settings |  | Frontend | Data Manager.AI | Aarthi | 2026-03-17 | 2026-03-19 | 2026-03-19 | Completed | 100
Develope the UI for global and study‑specific filtering within the Settings Configuration module of DataManager.ai | Developed the UI for global and study‑specific filtering within the Settings Configuration module of DataManager.ai, enabling users to filter configurations either globally or based on specific studies as needed |  | Frontend | DataManager.AI | Aarthi | 2026-03-18 | 2026-03-20 | 2026-03-20 | Completed | 100
Integrate Add config functionality UI and Global,study-specific UI | Integrate Aarthi's Data manager's UI functionalities such as Add config, Global and study specific settings |  | Frontend | Data Manager | Tejashree | 2026-03-19 | 2026-03-20 | 2026-03-20 | Completed | 100
Enable Severity Button Functionality in DQ Agent Backend Settings | Integrate backend logic to ensure the severity button in the DQ agent's settings configuration is fully operational. |  | Backend | Data Manager | Tejashree | 2026-03-19 | 2026-03-20 | 2026-03-19 | Completed | 100
Rules Engine for Reconciliation agent | Curated necessary rules engine to be applied on multiple dataset for the reconciliation agent |  | Documentation | Recon | Hanif | 2026-03-18 | 2026-03-18 | 2026-03-18 | Completed | 100
Integrate settings configuration code from Ruthra and Aarthi's branch | Merge the severity dropdown in the settings configuration and the dashboard ui from ruthra's branch into Aarthi's branch, resolve all merge conflicts, and then push the updated branch to Azure. |  | Frontend | DataManager.AI | Aarthi | 2026-03-19 | 2026-03-20 | 2026-03-20 | Completed | 100
Validate generated dataset for reconciliation agent | Dataset specifically curated for reconciliation agent to verify from multiple sources |  | DataBase | Reconciliation Agent | Hanif | 2026-03-19 | 2026-03-20 | 2026-03-26 | Completed
Azure Doc Intelligence | Updating PIT to Azure Doc Intelligence |  | Frontend/Backend | DataManager.AI | Ruthra | 2026-03-23 | 2026-03-27 | 2026-03-26 | Completed
Azure AI Foundry | Updating Protocol Check to use Azure OpenAI key |  | Frontend/Backend | DataManager.AI | Priyeshwar | 2026-03-23 | 2026-03-27 | 2026-03-26 | Completed | 100
Integrate Task Management table to the Task management section |  |  | Backend | Task Manager Agent | Tejashree | 2026-03-25 | 2026-03-26 | 2026-03-26 | Completed | 100
Test New Test Data on DQ Agent | Test the newly provided test data on the DQ Agent with data quality rule engine |  | Backend | Data Quality Agent | Tejashree, Aarthi | 2026-04-13 | 2026-04-16 |  | Completed | 100
Datamanager.AI and Dashboard Frontend | Refined the DataManager.AI frontend by adding checkboxes to the study selection dropdowns and implementing a delete‑confirmation popup. Also enhanced the Dashboard issues card to support selecting all studies or a specific study |  | Frontend | Datamanager.AI/Dashboard | Aarthi | 2026-03-27 | 2026-03-31 | 2026-03-30 | Completed | 100
Define New Test Data Rules for DQ Agent Validation | Document the data quality rules and validation criteria applied to test datasets used by the DQ agent |  | Backend | Data Quality Agent | Tejashree | 2026-03-31 | 2026-04-02 | 2026-04-02 | Completed | 100
Implement Multi-Study DQ Run with Toggle Awareness and Connect Dashboard Issues Card to the Database | Connect the DQ agent end‑to‑end with the study dropdown and toggle buttons to Backend and connect dashboard issues to db in which it displays all issues or filters them by selected studies based on the dropdown selection. |  | Backend | Data Manager.AI/Dashboard | Aarthi | 2026-03-31 | 2026-04-02 | 2026-04-02 | Completed | 100
Integrate Updated Protocol checks,Data fetch from Ruthra’s Branch into Priyesh Branch | Merge the Updated Protocol checks,Data fetch and Dq agents from Ruthra’s branch into Priyesh branch, resolve all merge conflicts, and then push the updated branch to Azure. |  | Backend | DataManager.AI | Priyeshwar | 2026-03-31 | 2026-04-01 | 2026-03-31 | Completed | 100
Populating Test Data | Populating test data in Azure postgres |  | DataBase | DataManager.AI | Ritesh | 2026-03-31 | 2026-04-01 | 2026-03-31 | Completed | 100
Storing Result of Protocol Check in issue table |  |  | Backend | Data Manager.AI | Ritesh, Priyeshwar | 2026-04-06 | 2026-04-10 | 2026-04-15 | Completed | 100
Restructuring DB SCHEMA |  |  | Backend | Data Manager.AI | Ruthra, Priyeshwar, Ritesh
Creating Rules Engine for DQ agent |  |  | Backend | Data Manager.AI | Tejashree,Aarthi | 2026-03-30 | 2026-04-02 | 2026-04-02 | Completed | 100
Reconciliation Agent |  |  | Backend | Data Manager.AI | Hanif | 2026-04-06 | 2026-04-17 |  | In Progress | 20
Task Manager Agent - Front end & backend - phase 1 |  |  | Backend | Data Manager.AI | Deepta C S | 2026-04-07 | 2026-04-17 |  | In Progress
Implement Study Filter Dashboard Feature | Move study dropdown to header and make Issues, Tasks, Open Queries all filter by study |  | Frontend/Backend | Dashboard | Aarthi | 2026-04-06 | 2026-04-08 | 2026-04-08 | Completed | 100
Flag Missing value, Out of range and invalid format detection for CTJ301UC201 study |  |  | Backend | Data Quality Agent | Tejashree | 2026-04-07 | 2026-04-09 | 2026-04-09 | Completed | 100
Data consistency for CTJ301UC201 study |  |  | Backend | Data Quality Agent | Aarthi | 2026-04-09 | 2026-04-10 | 2026-04-10 | Completed | 100
Add Toggle Buttons for protocol check |  |  | Frontend/Backend | Data Quality Agent | Priyeshwar, Ritesh | 2026-04-13 | 2026-04-17 |  | In Progress
Remove Groq Agent Code from DQ Agent for Study0001 | Remove all Groq agent related code, configurations, and references from the DQ agent file for Study0001 |  | Backend | Data Quality Agent | Tejashree | 2026-04-15 | 2026-04-16 | 2026-04-16 | Completed | 100
Rename open queries, Total Tasks in the Dashboard | Rename the labels of open queries to open query tasks and the tasks to Total tasks and the issues and Total issues |  | Frontend | Dashboard | Aarthi | 2026-04-15 | 2026-04-17 | 2026-04-16 | Completed | 100
Merge Dashboard UI and Backend from Teja’s Branch to DQ/Updated Branch | Integrated the Dashboard UI and backend changes from Teja’s branch into the DQ/updated branch |  | Frontend/Backend | Dashboard | Tejashree | 2026-04-15 | 2026-04-16 | 2026-04-15 | Completed | 100
Implement Issues Card to Include Reconciliation and Signal Detection Counts | Update the dashboard issues card to include and display issue counts from the reconciliation_issue and signal_detection tables in addition to the existing issues table count. |  | Backend | Dashboard | Tejashree, Aarthi | 2026-04-13 | 2026-04-17 |  | Completed | 100
Update DQ Agent Trigger to Use Refresh Button in Agent Section | Modify the DQ agent execution flow to use the Refresh button available in the DQ agent card under the Agent section instead of the existing Run DQ and Reconciliation button in the Data Manager tab. |  | Backend | Data Quality Agent | Tejashree, Aarthi | 2026-04-13 | 2026-04-17 | 2026-04-16 | Completed | 100
Azure AI Search Migration | Migrated from direct LLM calls to a RAG pipeline utilizing Azure AI Search for grounded analysis |  | Backend | PIT | Ruthra | 2026-04-06 | 2026-04-10 | 2026-04-12 | Completed | 100
PIT ICF Module Integration | Integrated the Informed Consent Form generation and interactive review workflow into the PIT UI. |  | Backend | PIT | Ruthra | 2026-04-10 | 2026-04-14 | 2026-04-14 | Completed | 100
Metadata & Study Sync | Automated extraction of study metadata and synchronization with the global Study Management tables. |  | Backend | PIT | Ruthra | 2026-04-08 | 2026-04-12 | 2026-04-13 | Completed | 100
Data & Blob Management | Configured Azure Blob Storage containers and database schemas for protocol persistence and security. |  | Backend | PIT | Ruthra | 2026-04-03 | 2026-04-06 | 2026-04-04 | Completed | 100
Merge Priyeshwar's branch into DQ/updated branch |  |  | Backend | Task Manager Agent | Tejashree, Aarthi | 2026-04-17 | 2026-04-20 | 2026-04-20 | Completed | 100
Study based filtering in the dashboard | Issues, Tasks, Open Queries all filter by specific selected study dynamically |  | Backend | Dashboard | Tejashree | 2026-04-17 | 2026-04-20 |  | Completed | 100
Updated Dashboard UI | Placed the active studies above the Open Query Tasks, tasks, issues card and removed the protocol Deviation card |  | Frontend/Backend | Dashboard | Tejashree | 2026-04-17 | 2026-04-20 |  | Completed | 100
Update Dashboard UI | Worked on implementing a Save button and checkbox selection for study-based filtering in the dashboard UI |  | Frontend | Dashboard | Aarthi | 2026-04-22 | 2026-04-24 | 2026-04-24 | Completed | 100
Implement Dashboard Reports Download | Implement functionality to allow users to download dashboard insights via the Reports button |  | Frontend/Backend | Dashboard | Aarthi | 2026-04-24 | 2026-04-30 |  | In Progress
Create new test dataset for DQ agent | Creating new test dataset with minimal number of dq issues to test DQ agent |  | Backend | Data Quality Agent | Tejashree | 2026-04-24 | 2026-04-29 |  | In Progress
Repository Refactoring & Cleanup | Consolidating the project structure, removing node_modules/dist artifacts, and flattening the agent file hierarchy. |  | Backend / Frontend / Agent | Maintenance | Ruthra | 2026-04-22 | 2026-04-24 | 2026-04-24 | Completed | 100
SDG.ai Module Integration & Azure Compatibility | Implementation of the Synthetic Data Generator (SDG) module, including the development of a dedicated API client, configuration modules for backend integration, and enabling dynamic routing. The module was also updated to ensure full compatibility with the Azure environment. |  | Backend / Frontend | Feature Implementation | Ruthra | 2026-04-20 | 2026-04-26 | 2026-04-27 | Completed | 100
PIT - Module Entirety Hardening | Complete general hardening and end-to-end integration of the PIT module, including PDF parsing, RAG query fallback, and ICF automation. |  | Feature / Bug Fix | PIT | Ruthra | 2026-05-18 | 2026-05-24 |  | Completed | 100%
Study Setup - Remove Study Progress | Remove the static/inactive "Study Progress" stepper and stats widgets from study setup panels. |  | Cleanup | Study Management | Ruthra | 2026-05-18 | 2026-05-20 | 2026-05-18 | Completed | 100%
Study Setup - Test/Check Site Data | Implement and test client-side validations, verification visual alerts, and modal improvements for site data setup. |  | Bug Fix | Study Management | Ruthra | 2026-05-18 | 2026-05-22 |  | Completed | 100%
Study Setup - Study Role Contacts | Setup study-based contacts filtering dynamically by target role (CRC, CRA, PI) isolated per trial. |  | Feature | Study Management | Ruthra | 2026-05-18 | 2026-05-23 |  | Completed | 100%
Study Setup - Clean Vendor/Service | Clean up seeded mock vendor configurations and remove obsolete services options. |  | Cleanup | Study Management | Ruthra | 2026-05-18 | 2026-05-21 | 2026-05-18 | Completed | 100%
Data Integration - Task Notifications | Link pending task creations and edits directly with in-app notification alerts and the system dispatcher. |  | Feature | Data Integration |  | 2026-05-18 | 2026-05-22 |  | Planned | 0%
Data Integration - Graph API Access | Refactor notification delivery to utilize the Microsoft Graph API SDK for enterprise email routing. |  | Infrastructure | Data Integration |  | 2026-05-18 | 2026-05-24 |  | Planned | 0%
Data Integration - Scheduler Hardening | Complete background scheduler engine loops to trigger ETL sync scripts automatically at defined intervals. |  | Feature | Data Integration |  | 2026-05-18 | 2026-05-23 |  | Planned | 0%
Data Integration - Dynamic Source Name | Add a dynamic datasource name parameter on integration setup to populate Trial Data Management dynamically. |  | Feature | Data Integration | Ruthra | 2026-05-18 | 2026-05-25 | 2026-05-18 | Completed | 100%
Trial Data - Remove Vendor Imaging | Remove the decommissioned "Vendor Imaging Data" tab trigger and grid components from Trial Data Management view. |  | Cleanup | Trial Data Management | Ruthra | 2026-05-18 | 2026-05-20 | 2026-05-18 | Completed | 100%
Reconciliation - Integrate to dev | Merge the updated data reconciliation checks, matching indices, and logic updates directly to the 'dev' branch. |  | Milestone | Reconciliation |  | 2026-05-18 | 2026-05-20 |  | Planned | 0%
Recon - Agentic Orchestration | Unify Reconciliation, Protocol Check, and Task Manager into a centralized DataManager Agent orchestration loop. |  | Feature | Orchestration |  | 2026-05-18 | 2026-05-26 |  | Planned | 0%
SDG.ai - Convert SDTM to CDASH | Change all occurrences of "SDTM" in the Synthetic Data Generator (SDG) page UI and configs to "CDASH". |  | Feature | SDG.ai | Ruthra | 2026-05-18 | 2026-05-19 | 2026-05-18 | Completed | 100%
Documentation from Deepta
Merge the Updated Branches - Push to DEV Branch
Workflow check - 1
Fixing Overall Bugs
DB Cleaning
Workflow check - 2 - New Data Ingestion
Note on B9: -Sequential Orchestration -Pipeline -Dynamic Orchestration -Router agent -Event-driven triggers

## Milestones
Milestone | Start Date | Target Date | Actual Complete Date | Status | Progress % | Comments | units
Milestone- details
Protocol Interpretation Tool | 2026-02-04 | 2026-04-15 | 2026-04-15 | Completed | 100
Protocol Generation Tool
Created Schema for Data Manager. | 2026-03-11 | 2026-03-13 | 2026-03-13 | Completed | 100
Dashboard | 2026-01-15 | 2026-01-15 | 2026-04-17 | Completed | 100
Study Management | 2026-01-29 | 2026-03-19 | 2026-03-19 | Completed | 100
Generating Test Data and Ingesting into DB | 2026-04-03 | 2026-04-06 | 2026-04-03 | Completed | 100
Data Integration |  | 2026-02-10 | 2026-02-09 | Completed | 100
Trail Data Management |  | 2026-02-24 | 2026-02-24 | Completed | 100
Data Fetch Agent | 2026-03-04 | 2026-03-10 | 2026-03-08 | Completed | 100
Data Quality (DQ) | 2026-04-06 | 2026-04-17 |  | Completed | 100 |  | total untis = 5 (4+ Unit test), completed = 4
Protocol Checks Agent | 2026-04-06 | 2026-04-17 |  | Completed | 100 | Facing few issues due to Agent hallucination | total untis = 6 (5+ Unit test)= 11, completed = 3
Reconciliation Agent |  | 2026-03-24 | 2026-04-17 | Completed | 100 | Created a Rules Doc of Reconciliation | total untis = 5 + Unit test= 5, completed = 9
Task Manager Agent | 2026-04-07 | 2026-06-04 |  | In Progress | 60 | Working with the updated flow, Whole Application UI Testing
Admin Module | 2026-04-24 | 2026-06-05 |  | In Progress | 70
Testing Agent Orchestration | 2026-06-05 | 2026-06-15 |  | In Progress | 80
DataManager.AI | 2026-04-07 | 2026-06-15 |  | In Progress | 60
ARCHICTURE | 2026-06-03 | 2026-06-05 |  | Not Started | 0 | Architecture diagram, Conceptual Flow, Operational Flow, Run Flow.
DB SCHEMA REBUILDING | 2026-06-05 | 2026-06-10 |  | Not Started | 0 | Db Cleaning, Fresh Workflow - New Data Ingestion
TESTING | 2026-06-08 | 2026-06-15 |  | Not Started

## Metrics
Metric | Count
Total Tasks | 148
Completed Tasks | 130
In Progress Tasks | 6
Not Started Tasks | 0
On Hold Tasks | 0
Overdue Tasks | 11
% Completion (Weighted by % Complete) | 69.38%

## Team Work Challenges
Date | Task | Task Details (issue details)- >24 hours | Who | Actions Tried (by own/help) | Resolved (Yes/No) | Resolved By? | Date resolved | Comment
2026-02-06 | Azure | Document Intelligence access issue | Hanif, Ruthra |  | Yes | Priyeshwar,Ruthra,Hanif,Ritesh |  | emails followup with Mitul
2026-02-06 | Azure | AI Foundry acces issue | Aarthi,Tejashree,Deepta |  | Yes
2026-02-18 | Azure | Web and backend Backend pipeline | Hanif | by own | Yes | Hanif | 2026-02-22
2026-02-18 | Azure | Agent pipeline not working- Protocol intrepretation | Priyeshwar, Sai Rithesh | by own | Yes | Priyeshwar,Ruthra,Hanif,Ritesh | 2026-02-24
2026-02-18 | Azure | Agent pipeline not working- Data Fetch issue | Priyeshwar, Sai Rithesh |  | Yes | Priyeshwar,Ruthra,Hanif,Ritesh
2026-02-25 | Azure | Package compatability issue- Protocol processing issue | Priyeshwar, Sai Rithesh |  | Yes | Priyeshwar,Ruthra,Hanif,Ritesh
2026-03-24 | Azure | Azure AI search access issue | Priyeshwar,Ruthra,Hanif,Ritesh |  | No |  |  | emails followup with Mitul
2026-04-15 | Visual Basic vide | free trial has only few prompts for vibe coding

## change request
Request Date | Item name | Description | Name | status | Code Merged? (Yes/No) | Pushed to azure | Date in azure | Comments
2026-04-14 | Dashboard | move the study filter to top next to reports | Aarthi | Done | Yes | yes | 2026-04-14
2026-04-14 | Dashboard | Rename the labels of open queries to open query tasks and the tasks to Total tasks and the issues and Total issues | Aarthi | Done |  | yes | 2026-04-16
2026-04-17 | Dashboard | remove create study in dashboard | Aarthi
2026-04-17 | Admin Module | system admin should set the communication method
2026-04-17 | Dashboard | downlodable reports for individual | Aarthi | In Progress
2026-04-17 | Dashboard | Run DataManager [option] | [5 empty] | what is thso
Configuration requirement UI
2026-04-24 | All studies selection checkbox | checkbox selection for study-based filtering in the dashboard UI | Aarthi | Done | yes | yes | 2026-04-27
UI Updation
View Document
DTS Structure
2026-04-27 | Task Management | Merged the updated code with Task Management | Deeptha | Done | Yes | Yes | 2026-04-27

## User Stories
Task/UserStory | Who | Assigned/Start date | Completed date | Status (done/ongoing/hold/issue/Not started) | Comments/Issue | issue date | Resolved (Y/N) | Resolved date
FE: Study List & Create Study UI | Ruthra | 2026-02-23 | 2026-02-24 | Done
FE: Study Details Page (Protocol Status + Requirements Status) | Hanif | 2026-02-23 | 2026-02-26 | Done
FE: Upload Protocol UI (PDF) + Progress | Hanif | 2026-02-23 | 2026-02-27 | Done
FE: Protocol Versions & Audit View | Hanif | 2026-02-23 |  | ongoing
FE: Requirements Graph Viewer (Read-only) |  |  |  | Not started
FE: “Generate Requirements” Button + Run Status |  |  |  | Not started
BE: Study CRUD APIs + Validation |  |  |  | Not started
BE: Protocol Upload: Blob Storage + Metadata Record |  |  |  | Not started
BE: Agent Job Framework for Protocol Processing (Webhook pattern) |  |  |  | Not started
BE: Requirements Graph Persistence Model + APIs |  |  |  | Not started
BE: WebSocket Notifications for Protocol/Requirements Jobs |  |  |  | Not started
AI: Protocol Chunking + Indexing Pipeline (Azure AI Search) |  |  |  | Not started
AI: Protocol → Requirements Graph Extraction (Study-specific) |  |  |  | Not started
AI: Requirements Schema Validator (Anti-hallucination Gate) |  |  |  | Not started
AI: Rule Catalog Bootstrap (Industry-standard driven) |  |  |  | Not started
BE: Create Oncology Test datasets | Aarthi, Tejashree | 2026-02-12 | 2026-02-13 | Done
BE: Create Oncology Protocol Document | Deepta | 2026-02-12 | 2026-02-13 | Done
BE: Populate the oncology data into the PostgreSQL database | Tejashree,Aarthi,Deepta | 2026-02-17 | 2026-02-20 | Done
BE: Develop DQ agent using rule engine | Tejashree,Aarthi,Deepta | 2026-02-17 | 2026-02-20 | Done
BE: Develop DQ agent using Protocol Document | Tejashree,Aarthi,Deepta | 2026-02-23 |  | Ongoing
BE: Supabase API Integration in Data Integration | Rithesh |  |  | ongoing | locally done
BE: Displaying Data in Trial Data Management from Azure PostgreSQL Database | Rithesh |  |  | Done
FE: Creating Protocol Interpretation Tab | Ruthra |  |  | Done
BE: Integrating Backend for PIT (Protocol Interpretation Tab) in Data Manager | Priyesh |  |  | Done
AI: Table Extraction in Protocol Interpretation | Ruthra |  |  | ongoing | locally done
AI: AI Analysis Report Generation in Protocol Interpretation | Priyesh |  |  | ongoing | locally done
AI: Uploading Multiple Protocols in Protocol Interpretation | Ruthra |  |  | ongoing | locally done
AI: Rule Analysis Generation in Protocol Interpretation | Priyesh |  |  | ongoing | locally done
BE: Integration Log Functional in Data Integration | Hanif | 2026-02-27 | 2026-03-03 | Done | locally done
BE: Enabling Filters in Integration Logs | Hanif | 2026-02-27 | 2026-03-03 | Done | locally done
BE: Displaying Log Details | Hanif | 2026-02-27 | 2026-03-03 | Done | locally done
BE: Enabling Filters in Integration Source | Rithesh | 2026-02-27 | 2026-03-03 | Done | locally done
BE: Making Actions Functional in Integration Source | Hanif | 2026-02-27 | 2026-03-03 | Done | locally done
BE: changing end points and reconfiguring the Database Tables | Ruthra | 2026-02-27 | 2026-03-03 | Done | locally done
FE: Removing Hardcoded values | Ruthra | 2026-02-27 | 2026-03-03 | Done | locally done
BE: Refactor the Data Integration code to run on azure | Priyesh | 2026-02-27 | 2026-03-03 | Done | locally done
BE: Adding Study_ID in Integration Source | Priyesh | 2026-03-04 | 2026-03-06 | Done | locally done
BE: Making Scheduler Funtional | Rithesh | 2026-03-04 | 2026-03-06 | Done | locally done
BE: Fixing the bugs in Integration Logs(Integration Source,Operation, & Status) | Priyesh | 2026-03-04 | 2026-03-06 | Done | locally done
BE: Making Data Fetch Agent Functional | Priyesh | 2026-03-09 | 2026-03-10 | Done
FE: Making Data Fetch Agent UI Functional | Priyesh | 2026-03-09 | 2026-03-10 | Done
FE: Removing CRI, Central Monitor.AI tab in UI | Priyesh | 2026-03-09 | 2026-03-10 | Done
BE: Fetching rules for Reconciliation | Rithesh | 2026-03-10 | 2026-03-13 | ongoing
BE: Validating data with the rules for Reconciliation | Rithesh | 2026-03-10 | 2026-03-13 | ongoing
FE: Making Reconciliation UI Funtional | Priyesh | 2026-03-10 | 2026-03-13 | ongoing
Rule checks configuration- separate selection for each study | Aarthi, Tejashree | 2026-03-02 | 2026-03-09
BE: Dynamic Severity Validation Engine | Ruthra | 2026-03-09 | 2026-03-11 | ongoing
FE: Dynamic Dashboard Data Integration | Ruthra | 2026-03-09 | 2026-03-11 | ongoing
BE: Creating new users login credentials for the Admin console | Hanif | 2026-03-10 | 2026-03-13 | ongoing
BE: Mapping new users with their Roles, Studies and Access management | Hanif | 2026-03-10 | 2026-03-13 | ongoing
BE: User management controls for System Admin | Hanif | 2026-03-10 | 2026-03-13 | ongoing
FE: adding ICF to PIT | Ruthra | 2026-04-07 | 2026-04-08 | Done
BE: adding ICF to PIT | Ruthra | 2026-04-07 | 2026-04-08 | Done
BE: moving ICF to Azure AI Search | Ruthra | 2026-04-10 | 2026-04-14 | Done

## Technical Skills
Names | React | Node | Python | AI prompts | Azure foundations | API prog
Aarthi L | Intermediate | Intermediate | Good | Good | Intermediate | Beginner
Deepta CS | Intermediate | Intermediate | Good | Good | Intermediate | Beginner
Hanif Mohammed | Beginner | Intermediate | Good | Good | Good | Beginner
Priyeshwar MD | Beginner | Intermediate | Good | Good | Intermediate | Beginner
Ruthravarshan S | Beginner | Beginner | Good | Good | Intermediate | Intermediate
Sai Ritheshwar | Beginner | Intermediate | Good | Good | Intermediate | Beginner
Tejashree | Intermediate | Intermediate | Good | Good | Intermediate | Beginner
Eswara | Intermediate | Intermediate | Good | Good | Good | Intermediate

## Accounts Mapped
Name | Account
Aarthi L | LV=
Deepta CS | Premier Research
Hanif Mohammed | Butterfly
Priyeshwar MD | LV=
Ruthravarshan S | Premier Research
Sai Ritheshwar | LV=
Tejashree | LV=

## Sheet3
Count of Status | Status
Tasks Category | Completed | In Progress | Not Started | (blank) | Grand Total
Backend |  | 1 | 17 |  | 18
Database | 2 | 4 |  |  | 6
Frontend | 2 | 3 |  |  | 5
(blank)
Grand Total | 4 | 8 | 17 |  | 29
llll

## Sheet7
Tasks Category | Completed | In Progress | Not Started
Backend |  | 1 | 17
Database | 2 | 4
Frontend | 2 | 3

## Sheet4
Assigned To | Count of Assigned To
Ritesh | 8
Ruthra/Hanif | 6
Arthi/Tejasree | 5
Priyeshwer | 4
Deepta | 2
Ruthra | 1
Aarthi | 1
Deepta/Tejashree | 1
Hanif | 1
Grand Total | 29

## Sheet5
Count of Assigned To | Status
Assigned To | Not Started | In Progress | Completed | Grand Total
Ritesh | 5 | 2 | 1 | 8
Ruthra/Hanif | 6 |  |  | 6
Arthi/Tejasree |  | 3 | 2 | 5
Priyeshwer | 3 | 1 |  | 4
Deepta | 1 |  | 1 | 2
Ruthra |  | 1 |  | 1
Aarthi | 1 |  |  | 1
Deepta/Tejashree | 1 |  |  | 1
Hanif |  | 1 |  | 1
Grand Total | 17 | 8 | 4 | 29

## Sheet6
Count of Tasks Category |  | Status
Tasks Category | Assigned To | Not Started | In Progress | Completed | Grand Total
Backend | Ruthra/Hanif | 6 |  |  | 6
| Ritesh | 5 |  |  | 5
| Priyeshwer | 3 | 1 |  | 4
| Deepta | 1 |  |  | 1
| Aarthi | 1 |  |  | 1
| Deepta/Tejashree | 1 |  |  | 1
Backend Total |  | 17 | 1 |  | 18
Database | Ritesh |  | 2 | 1 | 3
| Ruthra |  | 1 |  | 1
| Deepta |  |  | 1 | 1
| Hanif |  | 1 |  | 1
Database Total |  |  | 4 | 2 | 6
Frontend | Arthi/Tejasree |  | 3 | 2 | 5
Frontend Total |  |  | 3 | 2 | 5
Grand Total |  | 17 | 8 | 4 | 29

## Sheet1
Milestone | Status | Task Name | Task Description | Module | Assigned To | Task Status | %
Protocol Interpretation Tool | Completed | Code Conversion (FastAPI → NodeJS) | Convert FastAPI‑based Protocol Interpretation Tool code to NodeJS | PIT | Ruthra | Completed | 100
|  | Integrate PIT to Data Manager | Integrate the Protocol Interpretation Tool into the Data Manager module | PIT | Priyeshwar | Completed | 100
|  | Azure Doc Intelligence Integration | Update the Protocol Interpretation Tool to use Azure Document Intelligence for protocol parsing | PIT | Ruthra | Completed | 100
|  | Azure AI Foundry – Protocol Check Update | Update Protocol Check to use Azure OpenAI through Azure AI Foundry | PIT | Ruthra | Completed | 100
|  | Add ICF to PIT (FE & BE) | Add support for Informed Consent Form in both frontend and backend of the Protocol Interpretation Tool | PIT | Ruthra | Completed | 100
|  | Move ICF to Azure AI Search | Store and index Informed Consent Form data in Azure AI Search | PIT | Ruthra | Completed | 100
Study Management | Completed | Study Management – Core Functionality | Implement study creation and core study management functionality | Study Mgmt | Team | Completed | 100
|  | Study List & Create Study UI | Review and update the Study List and Create Study user interface | Study Mgmt | Ruthra, Priyeshwar | Completed | 100
|  | Study Details Page Backend Cleanup | Remove unwanted backend code from Study Management services | Study Mgmt | Hanif, Ritesh | Completed | 100
|  | Protocol Upload via Azure Blob | Connect Azure Blob Storage to upload and manage study protocols | Study Mgmt | Hanif | Completed | 100
|  | Nomenclature Refactor (Trials → Studies) | Refactor system terminology from Trials to Studies across the application | Study Mgmt | Ruthra | Completed | 100
Dashboard | Completed | Dynamic Dashboard Data Integration | Fetch and display live discrepancy and issue data dynamically from backend APIs | Dashboard | Ruthra | Completed | 100
|  | Display Total DQ Issues | Display total number of data‑quality issues on dashboard cards | Dashboard | Aarthi | Completed | 100
|  | Study‑based Filtering in Dashboard | Enable study‑based filtering of dashboard data | Dashboard | Aarthi | Completed | 100
|  | Study Filter in Header | Move the study selection dropdown to the dashboard header | Dashboard | Aarthi | Completed | 100
|  | Dashboard UI Refinements | Refine dashboard UI with checkboxes and delete confirmation pop‑ups | Dashboard | Aarthi | Completed | 100
Data Fetch Agent | Completed | Integrate Clinical Data to Fetch Agent | Ingest clinical trial data from the database into the Data Fetch Agent | Data Fetch | Tejashree | Completed | 100
|  | Execute Data Fetch Agent | Execute and validate the Data Fetch Agent pipeline end to end | Data Fetch | Priyeshwar | Completed | 100
|  | Integration Logs UI & Backend | Display, filter, and export data integration logs | Data Fetch | Priyeshwar, Hanif | Completed | 100
Data Quality (DQ) | In Progress | Missing Data Detection | Detect and flag missing or incomplete data fields | DQ Agent | Tejashree | Completed | 100
|  | Out‑of‑Range Detection | Identify and flag out‑of‑range values based on configured rules | DQ Agent | Tejashree | Completed | 100
|  | Invalid Format Detection | Detect and flag invalid data formats using rule‑based validation | DQ Agent | Aarthi | Completed | 100
|  | Data Consistency Checks | Identify and flag data inconsistencies across related fields | DQ Agent | Aarthi | Completed | 100
|  | Remove Groq Agent (Study0001) | Remove Groq agent code, configurations, and references for Study0001 | DQ Agent | Tejashree | In Progress | —
|  | Update DQ Trigger via Refresh Button | Modify DQ execution workflow to trigger using the Refresh button | DQ Agent | Tejashree, Aarthi | Not Started | —
Protocol Checks Agent | In Progress | Fetch Rules for Protocol Check | Fetch validation rules required for protocol checks | Protocol Check | Ritesh, Priyeshwar | Completed | 100
|  | Validate Data via Rules Engine | Validate clinical data against protocol‑defined rules | Protocol Check | Ritesh, Priyeshwar | Completed | 100
|  | Protocol Check UI Integration | Make the Protocol Checks user interface fully functional | Protocol Check | Priyeshwar | Completed | 100
|  | Toggle Buttons for Protocol Check | Add toggle buttons to enable or disable protocol checks | Protocol Check | Priyeshwar, Ritesh | In Progress | —
Reconciliation Agent | In Progress | Rules Engine Documentation | Define and document reconciliation rules and logic | Reconciliation | Hanif | Completed | 100
|  | Validate Reconciliation Dataset | Validate curated reconciliation datasets across multiple sources | Reconciliation | Hanif | Completed | 100
|  | Reconciliation Agent Backend | Implement backend logic for the Reconciliation Agent | Reconciliation
Task Manager Agent | In Progress | Issue‑to‑Role Mapping | Map data‑quality and reconciliation issues to roles using configuration logic | Task Manager | Deepta | Completed | 100
|  | Auto Task Creation from Issues | Automatically generate tasks from detected issues | Task Manager | Deepta | Completed | 100
|  | Role‑based Task Assignment | Assign tasks dynamically based on role‑based mapping | Task Manager | Deepta | In Progress | —
|  | Task Manager FE & BE – Phase 1 | Implement frontend and backend functionality for Task Manager Agent Phase 1 | Task Manager | Deepta | In Progress | —